## Task_Table1
Name | Duration | Start_Date | Finish_Date | Resource_Names
Market Assessment | 53.56 days | 2024 July 03 9:00 AM | 2024 September 16 2:30 PM
Evaluate market | 13.13 days | 2024 July 03 9:00 AM | 2024 July 22 10:00 AM | Melodee Beene
Develop Business opportunity | 8.94 days | 2024 July 22 10:00 AM | 2024 August 02 9:30 AM | Melodee Beene,Guy Radomski
Customer preference study | 25.63 days | 2024 August 02 9:30 AM | 2024 September 06 3:30 PM | Javier Ruddock
Business evaluation (NPV, etc.) | 5.88 days | 2024 September 06 3:30 PM | 2024 September 16 2:30 PM | Guy Radomski
Procurement | 95.5 days? | 2025 February 05 9:30 AM | 2025 June 18 2:30 PM
Identify vendors | 7.63 days | 2025 February 05 9:30 AM | 2025 February 14 3:30 PM | Tari Watrous
Develop and Issue RFQ | 6.5 days | 2025 February 14 3:30 PM | 2025 February 25 10:30 AM | Tari Watrous
Issue sample (production equivalent) | 5.88 days | 2025 March 12 4:30 PM | 2025 March 20 3:30 PM | Tari Watrous
Assess RFQ responses and select vendors | 10 days? | 2025 June 04 2:30 PM | 2025 June 18 2:30 PM
Supplier Quality | 53.88 days? | 2025 March 20 3:30 PM | 2025 June 04 2:30 PM
Perform supplier process capability | 20.88 days | 2025 March 20 3:30 PM | 2025 April 18 2:30 PM | Michael Holmberg
Approve sample parts | 8 days? | 2025 April 18 2:30 PM | 2025 April 30 2:30 PM
Qualify Supplier | 10 days? | 2025 May 21 2:30 PM | 2025 June 04 2:30 PM
Design | 70.38 days | 2024 September 16 2:30 PM | 2024 December 24 8:30 AM
Design and development plan | 6.88 days | 2024 September 16 2:30 PM | 2024 September 25 1:30 PM | Jessie Garoner
Design specs. | 26.13 days | 2024 September 25 1:30 PM | 2024 October 31 2:30 PM | Jessie Garoner
Identify testing requirements | 11.88 days | 2024 October 31 2:30 PM | 2024 November 18 1:30 PM | Jessie Garoner
Risk analysis | 13.38 days | 2024 November 18 1:30 PM | 2024 December 05 4:30 PM | Jessie Garoner
Design labeling | 6.38 days | 2024 December 06 1:30 PM | 2024 December 16 4:30 PM | Ted Zollinger
Approve design | 5.13 days | 2024 December 16 4:30 PM | 2024 December 24 8:30 AM | Ted Zollinger
Engineering | 113.63 days? | 2024 December 24 8:30 AM | 2025 May 30 2:30 PM
Initial engineering specs. | 5.75 days | 2024 December 24 8:30 AM | 2024 December 31 3:30 PM | Tyrone Sahota
Design verification activities | 4.19 days | 2024 December 31 3:30 PM | 2025 January 06 5:00 PM | Ted Zollinger,Tyrone Sahota
Verification design review | 2.38 days | 2025 January 07 8:00 AM | 2025 January 09 11:00 AM | Ted Zollinger,Tyrone Sahota
Release pre-production specifications | 6.13 days | 2025 January 09 11:00 AM | 2025 January 17 12:00 PM | Tyrone Sahota,Ted Zollinger
Build functional model | 22.13 days | 2025 January 22 2:30 PM | 2025 February 21 3:30 PM | Tyrone Sahota
Design validation activities | 5 days? | 2025 April 18 2:30 PM | 2025 April 25 2:30 PM
Validation design review | 4 days? | 2025 May 09 2:30 PM | 2025 May 15 2:30 PM
Approve model design | 4 days? | 2025 May 15 2:30 PM | 2025 May 21 2:30 PM
Design transfer activities | 7 days? | 2025 May 21 2:30 PM | 2025 May 30 2:30 PM
Engineering Quality | 95 days? | 2025 January 22 2:30 PM | 2025 June 04 2:30 PM
Evaluate design specifications | 12.25 days | 2025 January 22 2:30 PM | 2025 February 07 4:30 PM | Ted Zollinger
Develop testing protocol for prototype | 9.88 days | 2025 February 25 10:30 AM | 2025 March 11 9:30 AM | Tyrone Sahota
Test prototype | 10 days? | 2025 April 18 2:30 PM | 2025 May 02 2:30 PM
Evaluate results of tests and identify weaknesses | 6 days? | 2025 May 09 2:30 PM | 2025 May 19 2:30 PM
Product release meetings | 3 days? | 2025 May 30 2:30 PM | 2025 June 04 2:30 PM
Manufacturing | 68.5 days? | 2025 April 18 2:30 PM | 2025 July 24 9:30 AM
Process engineering plan | 15 days? | 2025 April 18 2:30 PM | 2025 May 09 2:30 PM
Develop production plan | 6 days? | 2025 May 21 2:30 PM | 2025 May 29 2:30 PM
Develop production control plan | 8.5 days? | 2025 June 04 2:30 PM | 2025 June 17 9:30 AM
Approve production parts | 5 days? | 2025 June 17 9:30 AM | 2025 June 24 9:30 AM
Contracting for deliveries | 8 days? | 2025 June 24 9:30 AM | 2025 July 04 9:30 AM
Submit production purchase order | 2 days? | 2025 July 04 9:30 AM | 2025 July 08 9:30 AM
Production pilot test | 5 days? | 2025 July 08 9:30 AM | 2025 July 15 9:30 AM
Debugging production system | 4 days? | 2025 July 15 9:30 AM | 2025 July 21 9:30 AM
Production release | 3 days? | 2025 July 21 9:30 AM | 2025 July 24 9:30 AM
Commercialization | 225.5 days? | 2024 September 16 2:30 PM | 2025 July 29 9:30 AM
Develop preliminary marketing plan | 2.88 days | 2024 September 16 2:30 PM | 2024 September 19 1:30 PM | Melodee Beene,Javier Ruddock
Develop marketing program | 8.69 days | 2024 September 19 1:30 PM | 2024 October 02 10:00 AM | Melodee Beene,Javier Ruddock
Train sales team | 25.88 days | 2024 October 31 2:30 PM | 2024 December 06 1:30 PM | Javier Ruddock
Advertising campaign | 16.38 days | 2024 October 31 2:30 PM | 2024 November 25 8:30 AM | Julie Schmitt,Melodee Beene
Show functional model at trade show | 3 days? | 2025 April 18 2:30 PM | 2025 April 23 2:30 PM
Product launch | 3 days? | 2025 July 24 9:30 AM | 2025 July 29 9:30 AM
Project Management | 272.06 days? | 2024 July 03 9:00 AM | 2025 July 18 9:30 AM
Project Management Period 1 | 26.38 days | 2024 July 03 9:00 AM | 2024 August 08 12:00 PM | Tari Watrous
Project Management Period 2 | 14.75 days | 2024 September 16 2:30 PM | 2024 October 07 11:30 AM | Tari Watrous
Project Management Period 3 | 14.75 days | 2024 October 31 2:30 PM | 2024 November 21 11:30 AM | Tari Watrous
Project Management Period 4 | 13.75 days | 2024 December 06 1:30 PM | 2024 December 26 10:30 AM | Tari Watrous
Project Management Period 5 | 15.88 days | 2024 December 31 3:30 PM | 2025 January 22 2:30 PM | Tari Watrous
Project Management Period 6 | 9.5 days | 2025 January 22 2:30 PM | 2025 February 05 9:30 AM | Tari Watrous
Project Management Period 7 | 11.63 days | 2025 February 25 10:30 AM | 2025 March 12 4:30 PM | Tari Watrous
Project Management Period 8 | 3 days? | 2025 April 18 2:30 PM | 2025 April 23 2:30 PM
Project Management Period 9 | 4 days? | 2025 May 09 2:30 PM | 2025 May 15 2:30 PM
Project Management Period 10 | 5 days? | 2025 May 21 2:30 PM | 2025 May 28 2:30 PM
Project Management Period 11 | 13 days? | 2025 June 04 2:30 PM | 2025 June 23 2:30 PM
Project Management Period 12 | 10 days? | 2025 July 04 9:30 AM | 2025 July 18 9:30 AM
Milestones | 225.5 days? | 2024 September 16 2:30 PM | 2025 July 29 9:30 AM
Milestone 1 | 0 days | 2024 September 16 2:30 PM | 2024 September 16 2:30 PM | Period 1 Training Costs[0],Period 1 Managerial Action Costs[0],Period 1 Unallocated Resource Costs[0]
Milestone 2 | 0 days | 2024 October 31 2:30 PM | 2024 October 31 2:30 PM | Period 2 Training Costs[0],Period 2 Managerial Action Costs[0],Period 2 Unallocated Resource Costs[0]
Milestone 3 | 0 days | 2024 December 06 1:30 PM | 2024 December 06 1:30 PM | Period 3 Training Costs[0],Period 3 Managerial Action Costs[0],Period 3 Unallocated Resource Costs[0]
Milestone 4 | 0 days | 2024 December 31 3:30 PM | 2024 December 31 3:30 PM | Period 4 Training Costs[0],Period 4 Managerial Action Costs[0],Period 4 Unallocated Resource Costs[0]
Milestone 5 | 0 days | 2025 January 22 2:30 PM | 2025 January 22 2:30 PM | Period 5 Training Costs[0],Period 5 Managerial Action Costs[0],Period 5 Unallocated Resource Costs[0]
Milestone 6 | 0 days | 2025 February 25 10:30 AM | 2025 February 25 10:30 AM | Period 6 Training Costs[0],Period 6 Managerial Action Costs[0],Period 6 Unallocated Resource Costs[0]
Milestone 7 | 0 days | 2025 April 18 2:30 PM | 2025 April 18 2:30 PM | Period 7 Training Costs[0],Period 7 Managerial Action Costs[0],Period 7 Unallocated Resource Costs[0]
Milestone 8 | 0 days? | 2025 May 09 2:30 PM | 2025 May 09 2:30 PM
Milestone 9 | 0 days? | 2025 May 21 2:30 PM | 2025 May 21 2:30 PM
Milestone 10 | 0 days? | 2025 June 04 2:30 PM | 2025 June 04 2:30 PM
Milestone 11 | 0 days? | 2025 July 04 9:30 AM | 2025 July 04 9:30 AM
Milestone 12 | 0 days? | 2025 July 29 9:30 AM | 2025 July 29 9:30 AM

## Resource_Table1
Name | Type | Initials | Max_Units | Standard_Rate | Overtime_Rate | Cost_Per_Use | Accrue_At | Base_Calendar
Guy Radomski | Work | G | 100% | $47.00/h | $70.50/h | 0 | Prorated | Standard
Melodee Beene | Work | M | 100% | $89.00/h | $133.50/h | 0 | Prorated | Standard
Tari Watrous | Work | T | 100% | $139.00/h | $208.50/h | 0 | Prorated | Standard
Javier Ruddock | Work | J | 100% | $50.00/h | $75.00/h | 0 | Prorated | Standard
Period 1 Training Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 1 Managerial Action Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 1 Unallocated Resource Costs | Material | P |  | $0.00 |  | 0 | Prorated
Jessie Garoner | Work | J | 100% | $72.00/h | $108.00/h | 0 | Prorated | Standard
Period 2 Training Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 2 Managerial Action Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 2 Unallocated Resource Costs | Material | P |  | $0.00 |  | 0 | Prorated
Julie Schmitt | Work | J | 100% | $44.00/h | $66.00/h | 0 | Prorated | Standard
Period 3 Training Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 3 Managerial Action Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 3 Unallocated Resource Costs | Material | P |  | $0.00 |  | 0 | Prorated
Ted Zollinger | Work | T | 100% | $59.00/h | $88.50/h | 0 | Prorated | Standard
Tyrone Sahota | Work | T | 100% | $48.00/h | $72.00/h | 0 | Prorated | Standard
Period 4 Training Costs | Material | P |  | $0.00 |  | 1752 | Prorated
Period 4 Managerial Action Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 4 Unallocated Resource Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 5 Training Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 5 Managerial Action Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 5 Unallocated Resource Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 6 Training Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 6 Managerial Action Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 6 Unallocated Resource Costs | Material | P |  | $0.00 |  | 0 | Prorated
Michael Holmberg | Work | M | 100% | $65.00/h | $97.50/h | 0 | Prorated | Standard
Period 7 Training Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 7 Managerial Action Costs | Material | P |  | $0.00 |  | 0 | Prorated
Period 7 Unallocated Resource Costs | Material | P |  | $0.00 |  | 0 | Prorated